## Sprint 01 User Stories
PRODUCT BACKLOG
# | USER | ACTION | EXPECTED OUTCOMES | ACCEPTANCE CRITERIA | STORY POINTS (Initial estimates only, to be re-reviewed and planned in detail) | PRIORITY | SPRINT (Initial estimates only, to be re-reviewed and planned in detail) | TEAM MEMBER | NOTES
1 | As a person in the neighbourhood, | I want to view all the activities or classes taking place in my neighbourhood, | so that I can participate and learn. | 1. All users should be able to view the activities on the calendar. 2. All activities should be displayed in a chronological order. 3. All activities must display title, related subject, date, time, and organisers details at the minimum. | 10 | High | One | Suchi Undevia | List activities functionality.
2 | As a person in the neighbourhood, | I want to view all the details of a particular activity such as location, materials required (paints, brushes for painting activity), | so that I can ensure I am able to attend and have the appropriate equipment. | 1. All users should be able to view the activity details once they click on more information. 2. Activity details should include organisers details. activity subject, date, and time at the minimum. 3. The activities should be displayed in a chronological order. | 4 | High | One | Chao Feng Huang | Brief description of the activity when clicked on from the calendar.
3 | As a senior person, | I want to arrange an activity or class for a subject of my interest, | so that I can share my knowledge and socialise with my neighbours. | 1. A senior user should be able to create an activity of their choice at a selected date and time. 2. The user must enter all the required information about the activity. 3. The activity should be displayed in the calendar. 4. The activity details should be recorded in the database. 5. All users should be able to view the activity once it is created. | 20 | High | One | Avantika Karki | Booking an activity.
4 | As a senior person, | I want to add information on materials to bring when arranging an activity, | so that everyone attending is able to participate in the activity. | 1. The organiser should be able to add the information on required equipment when creating the activity. 2. All users should be able to view the required/ suggested equipment needed for the class or activity. | 2 | Low | One | Suchi Undevia | Items to bring for an activity (books, sketch pads etc).
5 | As a senior person, | I want to add a brief description about the activity I am arranging, | so that everyone can get a brief understanding of what is involved. | 1. The organiser should be able to add a brief description of the activity to inform all users. 2. The interested user should be able to view the description in order to make a decision to attend. | 2 | Medium | One | Avantika Karki | Adding a description of the activity.
6 | As a senior person, | I want to add location and contact details when arranging an activity, | so that everyone attending knows where to arrive. | 1. The users who have elected to attend an activity should be able to see the organisers contact details and address as well as the time the activity begins. | 6 | High | One | Avantika Karki | Adding location details.
7 | As a senior person, | I want to get feedback on how my previous activity was received, | so that I can make improvements when planning future activities. | 1. The attendees of the activity should be able to rate the event. 2. The organiser of the class should be able to view the rating given. 3. All user should be able to see the rating given to a specific activity. | 10 | Low | Three | Avantika Karki | Feedback or rating.
8 | As a senior person, | I want to be able to delete an activity I previously arranged, | so that in case of unforeseen circumstances, I don't inconvenience everyone. | 1. A user should be able to delete an activity that he/she organised. 2. The calendar should be updated to show the deleted activity. 3. The user must have created an activity to be able to delete it. 4. A user cannot delete another user's activity. | 5 | High | Two | Chao Feng Huang | Deleting an activity.
9 | As a person in the neighbourhood, | I want to only view the activities or classes I am interested in, | so that I don't have to spend a long time searching through the classes. | 1. Display a set of categories of subjects. 2. The user can select from the category which leads to only displaying activities related to the specific subject. | 3 | Medium | Two | Suchi Undevia | Calendars arranged according categories.
10 | As a senior person, | I want the website to be easy to use and see, | so that I can use it frequently and by myself. | 1. The user interface is very simple. 2. The user interface includes colours to aid in differentiating different links and functionalities of the web application. 3. The user interface has large clear font. | 4 | High | Three | Chao Feng Huang | User interface design (large font, simple interface etc).
11 | As a person in the neighbourhood, | I want to view the neighbourhood news or announcements, | so that I am informed of all the activities taking place near me. | 1. A user should be able to view the latest announcements and news on the related webpage. 2. Typically updated by the site administrator. 3. Site administrators contact details should be displayed at the bottom for users who wish to publish announcements. 4. The announcements should be displayed in chronological order. 5. Relevant images should be uploaded with the announcements. 6. Clear division should appear between the announcements to differentiate the items. 7. The announcements much have a publishing date displayed so the users are informed. | 5 | Low | Three | Suchi Undevia | Announcements Webpage.
12 | As a person in the neighbourhood, | I want to notify the person organising the activity that I am attending, | so that I can ensure the class doesn't get full and I have a seat. | 1. A notification should be issued to the organiser when another user wishes to attend a class. 2. The user attending the class should also see a confirmation message once they have elected to attend the class. | 5 | High | Two | Chao Feng Huang | Number of people attending.
13 | As a senior person, | I want to know how many people are attending my activity or class, | so that I can ensure I have enough space and equipment. | 1. A user should be able to identify how many attendees are coming to the class. | 3 | Medium | Two | Avantika Karki | Set the number of people attending.
14 | As a site visitor, | I want to know about the website and view the frequently asked questions, | so that I can easily confirm authenticity of the website and its purpose. | 1. A user should be able to view brief information on the purpose of the website and its functionality. 2. The user should be able to see the frequently answered questions so they do not need to contact the site administrator for smaller, less complex queries. | 4 | Low | Three | Chao Feng Huang | FAQ and about page.
15 | As a senior person, | I want to create an account, | so that I can manage arranging activities or classes. | 1. A user should be able to enter the required information and register an account. 2. A user should be informed when the account registration is successful. 3. Records should be created when a user creates an account in the relevant tables. 4. If the account creation is unsuccessful, the error message displayed should include site administrator's details for the user. 5. With successful account registration the user should be redirected to the login page. 6. Any validation on user data that is required should take place before recording in the database. | 20 | High | One | Suchi Undevia | Create an account.
16 | As an account holder, | I want to view my account information, | so that I can view the information I have previously provided. | 1. A user should be able to view all the submitted/ recorded account details. 2. A user should be able to view any files they have uploaded, including images. | 9 | High | One | Avantika Karki | View an account.
17 | As an account holder, | I want to delete my account, | so that I can have control over my information. | 1. A user should be able to delete their account. 2. The database should remove the registered user's details and any other entries. 3. A confirmation prompt should appear for the user to confirm deletion. 4. A confirmation message is required to be displayed or the user. 5. If an error occurs, the site administrators details should be displayed to the user for troubleshooting. 6. A user must have an account in order to delete it. | 7 | Medium | One | Chao Feng Huang | Delete an account.
18 | As an account holder, | I want to update my account details, | so that I can maintain most up-to-date contact information. | 1. User should be able to update contact details and their address. 2. User should be able to update their personal details including name or age. 3. The updated details should be updated in the database. 4. A confirmation message should be displayed once the database is updated to the user. 5. If an error occurs, the site administrators details should be displayed to the user. | 5 | Medium | One | Suchi Undevia | Update an account.
19 | As an account holder, | I want to upload my photo, | so that people attending my class are familiar with me. | 1. User should be able to upload a photo while creating their account. 2. Photo should be displayed in the account information webpage. 3. Photo should be displayed to the attendants if I have an activity planned. | 2 | Low | One | Chao Feng Huang | Upload a photo.
20 | As an account holder, | I want to use a username and password to login to my account, | so that I can be assured of its security. | 1. User should not be able to login if they are not registered under the user database. 2. User should not be able to login with username only. 3. User should not be able to login with a password only. 4. User should not be able to login until they click the submit button. 5. If an issue occurs, the error message should display site administrators details to troubleshoot the issue. | 2 | High | One | Avantika Karki | Login functionality.
21 | As a person in the neighbourhood, | I want to view all the local businesses in the neighbourhood, | so that I can support local businesses. | 1. A web page should display all the local businesses of the neighbourhood. 2. Site administrators details should be displayed if a local business wants to be listed on the page. 3. A brief description of the business, their contract details, and their address should be provided. 4. An image of the business should be displayed for the users for better recognition. | 4 | Low | One | Avantika Karki | Web Page listing the local businesses.
22 | As a site administrator, | I want to provide my details and a site map, | so that people can approach me for information or improvements to site. | 1. Site information page should display the site administrators details. 2. A site map should be included to give user an overview of the web application. | 3 | Low | One | Chao Feng Huang | Site map and administrator details.
23 | As a site administrator, | I want to only want people over 64 to be able to arrange activities, | so that the focus of the website remains on senior members of the community and other users can create account and attend classes. | 1. User has to enter his/ her age when creating an activity thus ensuring the person creating an activity is over 64. 2. If the user enters an age below 64, a message should be displayed to inform the user of restriction and its purpose. | 3 | High | One | Avantika Karki | Age limit on activity booking.
24 | As a site administrator, | I want to save all the user information in a database to support user account functionality, | so that they can be accessed by the website users. | 1. The database is able to save all the user related data in appropriate columns and tables. 2. A record or multiple records are created in the relevant tables when a user creates an account. 3. All the user related data can be retrieved from the database when required. | 20 | High | One | Suchi Undevia | Database tables for users.
25 | As a site administrator, | I want to save all the information on the scheduled activities, | so that it can be accessed by the users and viewed anytime. | 1. Database is able to save all the activity related data in appropriate columns and tables. 2. All activity related records are viewable and accessible. 3. A record or multiple records are created when an activity is created. | 10 | High | One | Suchi Undevia | Database tables to store activity information.
26 | As a person in the neighbourhood, | I want to attend activities that are close to my house, | so that I do not have to travel long distance and depend on someone to drive me. | 1. All activities should display location. 2. All calendars should spilt up according to suburb locations. 3. A calendar should only display activities related to the selected suburb. | 4 | High | One | Suchi Undevia | Database requires a table for suburbs.
27 | As an account holder, | I want the web application to remember my suburb preference, | so that I do not have to choose it every time I search for activities. | 1. The user profile should include preferences for posting activities in a specific suburb. 2. The user profile should include preferences for attending activities in a specific suburb. 3. The user profile should record the home suburb of the user. | 3 | Low | One | Avantika Karki | The database table that records user profiles should include suburb preference.
28 | As a new site visitor, | I want to use my google account to login to this website, | so that I do not have to manage separate accounts. | 1. Google authentication should be present on the sign-up and login pages. 2. A user account and profile should be created so that the user can see a standard account. | 6 | Low | One | Chao Feng Huang | Adding third party authentication.
29 | As an account holder, | I want to link my social media accounts to may account here, | so that I can switch between them and post related activities on other platforms. | 1. Facebook account connection should be seen under user profile. 2. These connections should be optional. | 20 | Low | One | Suchi Undevia | Adding third party integration. Further research required.
30 | As a site visitor, | I want to search for member profiles by name, | so that I can find others to connect with. | 1. Navigation bar should display an option to search for members. 2. A search should display correct results. | 4 | Medium | One | Suchi Undevia | Search functionality and database query.
31 | As a site visitor, | I want to mark my profile as private, | so that others can only see my name and not other information I do not want shared. | 1. A user should be able to update an option to make their profile private or public. 2. A profile should only display a username of the user if the private option is selected. | 6 | Low | One | Avantika Karki | Business login needs to be added to ensure this functionality as well as an Boolean attribute in the user profile table.
32 | As a site visitor, | I want to mark my contact details as private, | so that even though my other information is public my contact details remain private so no one can get in touch. | 1. A user should be able to update an option to make their contact details private or public. 2. A user's profile should not display contact details to other users if they have elected to keep their details private. 3. A user's profile should display contact details if they have choose to keep them as public. | 5 | Low | One | Avantika Karki | Business login needs to be added to ensure this functionality as well as an Boolean attribute in the user profile table.
33 | As a site administrator, | I want to be able to have access to any member's profile, | so that I can trouble shoot any issues they may be having. | 1. The administrator should be able to make changes to a member's profile without using the members login details. | 6 | Medium | One | Chao Feng Huang | Admin control panel to be set up as well as database access should be available to the administrator.
34 | As a site visitor, | I want to be able to fill a form to submit news stories to the administrator, | so that they can be published on the website's news page. | 1. An option to submit news should be available if the user is logged in. 2. A form should be displayed to enter the details of the news. 3. The administrator should receive an email once the form is submitted (success or an error) | 10 | Low | One | Suchi Undevia | SendGrid, email notification, and form to be set up to capture the information.
35 | As a site visitor, | I want to search through the archives on the website for old news stories, | so that I can access items from the past that I may not recall but, require the details. | 1. An archive webpage should be set up. 2. The archive webpage link should be visible on the navigation bar. 3. The archive webpage should include a search functionality (date, month, year, keywords). 4. It should display older stories previously published on the website according to the filtering criteria. | 20 | Low | One | Suchi Undevia | Database tables need to be set up for recording news stories. And archive webpage and search functionalities to be developed.
36 | As an account holder, | I want to subscribe to the news on the website, | so that I can get an email notification every time new news stories have been added. | 1. A user profile should include an option to subscribe to news stories. 2. If a user has subscribed to a news story then they should receive an email notification with a message of updated news. 3. A user should not receive emails if they have not subscribed to the news stories. | 10 | Low | One | Chao Feng Huang | Database table to be updated and email functionality to be added.
37 | As a new site visitor, | I want to be able to do a keyword search on the FAQ page, | so that I don't have to spend a long time searching through the listed questions. | 1. A user should be able to search through the FAQs with certain keywords. 2. A message should be displayed if the search is unsuccessful. 3. Relevant results should be displayed if the keyword search returns results. 4. Site administrators contact details should be displayed so the user can get in touch if the search is unsuccessful. | 3 | Low | One | Chao Feng Huang | Database table to store the questions. Adding a search functionality.
38 | As an account holder, | I want to see the location of an activity on a google map, | so that I can visualise the distance and understand the location better. | 1. The activity details page should display the google map with the location of activity marked. 2. The location of the activity marked on the map should be visible to everyone on the website. 3. The location of the activity marked on the map should be the same as the one specified by the organiser. | 10 | Medium | One | Suchi Undevia | Google map API integration.
39 | As an account holder, | I want to receive an email notification a day before the activity I am attending, | so that I don't have to set my own reminders. | 1. Only the members attending an activity should receive a notification. 2. The notification should include all the relevant activity details (location, materials required, organiser's details etc). | 8 | Low | One | Chao Feng Huang | Reminder and email functionality to be setup.
40 | As an account holder, | I want to view all the activities I previously attended, | so that I can recall the details and the information. | 1. A user profile should include an option to view the attended activities. 2. The list of activities should only included the ones which the user attended. | 5 | Low | One | Avantika Karki | Webpage to be set up to display all previously attended activities.
41 | As an account holder, | I want to view all the activities I previously organised, | so that I can recall the details and the information. | 1. A user profile should include an option to view the organised activities. 2. The list of activities should only included the ones which the user planned. | 5 | Low | One | Avantika Karki | Webpage to be set up to display all previously organised activities.
42 | As an account holder, | I want to add relevant images when I am organising an activity, | so that I can provide more information to other members who may be interested. | 1. A user should be able to upload images when creating an activity. 2. A message should be displayed to remind users not to upload inappropriate images. | 4 | Low | One | Avantika Karki | Activity table should include an option to upload an image.
43 | As an account holder, | I want the news stories to be marked "read" once I have seen them, | so I know which news stories I have finished reading and which are pending. | 1. The previously opened news stories should be displayed in a different colour to show they have been read when a user is logged in. 2. The remaining user stories should be displayed in standard colour to show they haven't been opened. | 4 | Low | One | Chao Feng Huang | Formatting and tracking. Further research required.
44 | As an account holder, | I want to add external links to relevant material when organising an activity, | so that the interested members can do their own research. | 1. The activity details page should display the external links provided by the organiser. 2. The organiser should be able to add the links when filling out the plan an activity form. 3. When a member clicks on the link they should be redirected to the correct information. | 3 | Low | One | Suchi Undevia | Update database table and form.
45 | As a new site visitor, | I want to be able to read the privacy policy, | so that I can be assured of its security. | 1. Home page should have a link to the privacy policy of the website. | 3 | Low | Five | Chao Feng Huang | Add the webpage.
46 | As an account holder, | I want to be able to add a short message that all members can see, | so that I can voice my thoughts and do not have to send an official announcement through the site administrator. | 1. A logged in user should be able to posts a small message in the neighbourhood forum. 2. The message should be displayed to all members. 3. A user must be logged in to see the messages. 4. A user must be logged in to post the messages. | 5 | Low | Six | Suchi Undevia | Add the webpage and database table.
47 | As an account holder, | I want to post a comment about the activity I attended, | so that all members can find out about how good the activity was. | 1. The activity details page should display a comments section. 2. A user should be logged in to post a comment. 3. A user should be able to ask questions in the commenting area to the organiser. 4. The organiser should be able to view all comments. 5. A comments should always be displayed in a chronological order. 6. The organiser should be able to delete a comment. 7. The user should be able to delete a previously posted comment. | 10 | Low | Six | Avantika Karki | Add the comments functionality and database table.
48 | As a site visitor, | I want to know how many members have an account, | so that I know how many people are using the website. | 1. The home page should display the number of accounts registered. | 2 | Low | Six | Avantika Karki | Total number of accounts displayed.
49 | As a site visitor, | I want to know how many website users are currently logged in to their account, | so that I know how many people visit the site everyday. | 1. The home page should display the number of accounts active currently. | 3 | Low | Six | Avantika Karki | Total number of accounts with the status logged in.
50 | As a senior person, | I want the error messages to be very descriptive, | so that I know what are the next steps to take when I am unfamiliar with a new website. | 1. All error messages should include polite and clear messages. 2. All error messages should have site administrators details so they can be contacted. 3. Should include step by step guide where required. | 2 | Low | Six | Chao Feng Huang | Review all error messages.
51 | As a site visitor, | I want logical and clear URLs, | so that the application feels clear and transparent. | 1. URL patterns should be simple | 2 | Low | Six | Suchi Undevia | Establish simple paths patterns.
| PRIORITY | RATIONALE |  | 1 STORY POINT = 1 Hour of Team Member's Time
| High | User stories that support the core purpose and functionalities for the web application. Focused on value driven approach. These stories provide the highest value as well as support the minimum viable product. |  | ESTIMATE: These are initial estimates only. To be discussed further during sprint planning.
| Medium | User stories that provide primary and secondary information about users and activities which are essential for effectiveness of the website.
| Low | User Interface design elements, static content, and basic visitor information.

## Product Vision
PRODUCT VISION
| Team Name: | 2+2=5
| Team Members: | Chao Feng Huang | 1391571
|  | Avantika Karki | 1499258
|  | Suchi Undevia | 1369059
| Topic: | “Online web application for local senior people to share their knowledge, help each other, organise activities, and find useful information in just simple clicks”
| Situation: | More and more senior people feel lonely at home, especially after they have retired from work. Monotonous routines and lack of social connectivity can lead to health issues in the long-term, whereas an engaged environment can prevent such problems and provide a proactive approach to their retired life
| Opportunity: | For senior people who are living in the same community, they can share their hobby or skill within their neighbourhood and make new friends who have the same interest. They can find useful information, such as latest announcements, news stories on health related issues, as well as organise and join local activities by searching the calendar. It provides them with a platform to engage with neighbours of all ages.
| Critical Problem: | How to interact, communicate, and facilitate a better lifestyle for senior people in the neighbourhood?
| Vision Statement: | FOR a senior person WHO wants to share their skills, learn from others while engaging with the neighbours THE Grown-Up Next-Door IS A web application THAT allows senior people within the local community to make friends, share interests, organise, and join activities and find useful local information promptly. UNLIKE other applications or platforms that are too complex to use and not focusing on senior people.

## Entity Relationship Diagrams
CONCEPTUAL AND LOGICAL ENTITY RELATIONSHIP DIAGRAMS
Draft interpretation of database tables required (Sprints 1-3 only)